# **Milestone 1: Completing the Global Treps application and Donation tracking system by October 20th, 2023.**

**Specific**: Develop a centralized website and application to facilitate shark tank events and promote entrepreneurship.

**Measurable**: The website and application must meet all specified requirements and functionalities outlined in the project objectives.

**Assignable**: UI Developer Bobby, UX Designer Kim, Technical Support Vishal, and Graphic Designer, Ashwath, will collaborate to design and develop the website and application.

**Realistic**: With the allocated budget and resources, developing a functional website and application by the specified date is feasible.

**Time-Framed**: The website and application will be completed on or before October 20th, 2023.

# **Milestone 2: Completing the first shark tank event by November 1st, 2023.**

**Specific**: Organize and conduct the first shark tank event to give entrepreneurs a platform to pitch their ideas to investors.

**Measurable**: The first shark tank event must have a minimum of 20 participants and attract at least 50 potential investors.

**Assignable**: Ashok, the Event Organizer, will coordinate all aspects of the event, including participant registration, venue booking, and investor invitations.

**Realistic**: Given the allocated budget and timeline, organizing the first shark tank event with 20 participants and 50 investors is achievable.

**Time-Framed**: The event will occur on or before November 1st, 2023.

# **Milestone 3: Completing the second shark tank event by November 14th, 2023**.

**Specific**: Conduct the second shark tank event to promote entrepreneurship and connect investors with innovative ideas.

**Measurable**: The second shark tank event should have a minimum of 25 participants and engage at least 60 investors.

**Assignable**: Ashok, the Event Organizer, will again coordinate all aspects of the second event, just like Milestone 1.

**Realistic**: Building on the first event’s success, achieving higher participation and investor engagement for the second event is feasible.

**Time-Framed**: The event will occur on or before November 14th, 2023.

# **Milestone 4: Completion of the third shark tank event by November 27th, 2023.**

**Specific**: Organize the third shark tank event, maintaining momentum and engagement from previous events.

**Measurable**: The third shark tank event should have a minimum of 30 participants and attract at least 70 investors.

**Assignable**: Ashok, the Event Organizer, will continue to be responsible for coordinating all aspects of the third event.

**Realistic**: Building on the success of the previous events, achieving higher participation and investor engagement for the third event is reasonable.

**Time-Framed**: The event will occur on or before November 27th, 2023.

# **Milestone 5: Completing the fourth shark tank event by December 8th, 2023.**

**Specific**: Organize the final shark tank event to culminate the Global Treps Project successfully.

**Measurable**: The fourth shark tank event should have a minimum of 35 participants and engage at least 80 investors.

**Assignable**: Ashok, the Event Organizer, will continue to lead the planning and execution of the final event.

**Realistic**: By consistently building on the success of previous events, achieving higher participation and investor engagement for the fourth event is attainable.

**Time-Framed**: The event will occur on or before December 8th, 2023.