## Risk Register
Risk Register for Global Treps
Date : 8/4/2023
| Project Name: |  | Global Treps Project
| ID No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Risk Score | Status
| R01 | 1 | Ineffective Communication with Dr.B | Because of common communication (text messaging) challenges with Dr. B may lead to misunderstood details about the event or supply chain issues. | Communication | Alfreda's communication medium | Lack of response from Dr.B | Schedule regular calls or Team meetings with Dr. B to clarify all important details. Use email to follow up and confirm key discussions. | Alfreda | High | High | 81 | Nithya Ganesan(PM) will set up the meeting with in a week
| R02 | 2 | Delay in Video Editing Task | Because of Ashok's wrist injury, he cannot work on the project for three weeks leading to project disruption. | Schedule | Ashok's Wrist injury | Ashok's inability to work | Reassign the task to other team members. | Nithya Ganesan | Low | Medium | 14 | Nithya Ganesan(PM) will assign the task to Angela
| R03 | 3 | Inexperienced users of Kanban Board | Because of Bobby, who is the only available resource who utilizes Kanban boards leading ineffective team collaboration | Team Collaboration | Adoption of Kanban Boards | Clear responsibilities were not set | Motivating all team members to use kanban boards | Nithya Ganesan | Medium | Medium | 36 | Nithya Ganesan(PM) and Bobby will schedule KT calls to effectively utilize kanban boards
| R04 | 1 | Additional Sponsor Backing | Because of additional sponsor support beyond the initial commitments, leads to increase in funding for the project. | Financial | Networking | Positive performance during shark tank events | Sponsor engagement and continuous support for the project. | Nithya Ganesan | Low | High | 27 | Nithya Ganesan(PM) to schedule weekly meetings with sponsors to provide regular updates
| R05 | 2 | High Media Coverage and Publicity | Because of Significant Media attraction leading to widespread coverage | Promotion | Sucessfull implemenation of project | Positive performance during shark tank events | Usage of Media coverage to promote future shark tank events | Alfreda | Low | High | 24 | Alfreda to publish the media coverage of shark tank events in the org's social media
| R06 | 3 | Event Planning | Because of the challenges in communication with Dr. B, Alfreda seeks the input of other stakeholders, leading to better event planning. | Stakeholder management | Communication issues with Dr. B | Engaging other stakeholders for input | Gather inputs from various stakeholders to improve event planning | Alfreda | Medium | Medium | 30 | Alfreda meets with other stakeholders to plan the events effectively.